## Slide 1: SOFTWARE PROJECT PLANNING REKAYASA PERANGKAT LUNAK CSG2J3
by : Tim Pengajar RPL
Teknik Informatika – Telkom University

## Slide 2: Outline
Project Planning
Scope and Feasibility
Project Resources
Estimation of Project Cost and Effort

## Slide 3: Project Planning

## Slide 4: Software Project Planning
Software project planning encompasses five major activities
  Estimation, scheduling, risk analysis, quality management planning, and change management planning
Estimation determines how much money, effort, resources, and time it will take to build a specific system or product
The software team first estimates
  The work to be done
  The resources required
  The time that will elapse from start to finish
Then they establish a project schedule that
  Defines tasks and milestones
  Identifies who is responsible for conducting each task
  Specifies the inter-task dependencies

## Slide 5: Observations on Estimation
Planning requires technical managers and the software team to make an initial commitment
Process and project metrics can provide a historical perspective and valuable input for generation of quantitative estimates
Past experience can aid greatly
Estimation carries inherent risk, and this risk leads to uncertainty
The availability of historical information has a strong influence on estimation risk

## Slide 6: Observations on Estimation (continued)
When software metrics are available from past projects
  Estimates can be made with greater assurance
  Schedules can be established to avoid past difficulties
  Overall risk is reduced
Estimation risk is measured by the degree of uncertainty in the quantitative estimates for cost, schedule, and resources
Nevertheless, a project manager should not become obsessive about estimation
  Plans should be iterative and allow adjustments as time passes and more is made certain

## Slide 7: Task Set for Project Planning
Establish project scope
Determine feasibility
Analyze risks
Define required resources
  Determine human resources required
  Define reusable software resources
  Identify environmental resources
Estimate cost and effort
  Decompose the problem
  Develop two or more estimates using different approaches
  Reconcile the estimates
Develop a project schedule
  Establish a meaningful task set
  Define a task network
  Use scheduling tools to develop a timeline chart
  Define schedule tracking mechanisms

## Slide 8: Scope and Feasibility

## Slide 9: Software Scope
Software scope describes
  The functions and features that are to be delivered to end users
  The data that are input to and output from the system
  The "content" that is presented to users as a consequence of using the software
  The performance, constraints, interfaces, and reliability that bound the system
Scope can be define using two techniques
  A narrative description of software scope is developed after communication with all stakeholders
  A set of use cases is developed by end users

## Slide 10: Software Scope (continued)
After the scope has been identified, two questions are asked
  Can we build software to meet this scope?
  Is the project feasible?
Software engineers too often rush (or are pushed) past these questions
Later they become mired in a project that is doomed from the onset

## Slide 11: Feasibility
After the scope is resolved, feasibility is addressed
Software feasibility has four dimensions
  Technology – Is the project technically feasible? Is it within the state of the art? Can defects be reduced to a level matching the application's needs?
  Finance – Is it financially feasible? Can development be completed at a cost that the software organization, its client, or the market can afford?
  Time – Will the project's time-to-market beat the competition?
  Resources – Does the software organization have the resources needed to succeed in doing the project?

## Slide 12: Project Resources

## Slide 13: Resource Estimation
Three major categories of software engineering resources
  People
  Development environment
  Reusable software components
    Often neglected during planning but become a paramount concern during the construction phase of the software process
Each resource is specified with
  A description of the resource
  A statement of availability
  The time when the resource will be required
  The duration of time that the resource will be applied
Time window

## Slide 14: Categories of Resources
People
Number required
Skills required
Geographical location
Development Environment
Software tools
Computer hardware
Network resources
Reusable Software Components
Off-the-shelf components
Full-experience components
Partial-experience components
New components
The
Project
Notes: Off-the-shelf components
  Components are from a third party or were developed for a previous project
  Ready to use; fully validated and documented; virtually no risk
Full-experience components
  Components are similar to the software that needs to be built
  Software team has full experience in the application area of these components
  Modification of components will incur relatively low risk
Partial-experience components
  Components are related somehow to the software that needs to be built but will require substantial modification
  Software team has only limited experience in the application area of these components
  Modifications that are required have a fair degree of risk
New components
  Components must be built from scratch by the software team specifically for the needs of the current project
  Software team has no practical experience in the application area
  Software development of components has a high degree of risk

## Slide 15: Estimation of Project Cost and Effort

## Slide 16: Factors Affecting Project Estimation
The accuracy of a software project estimate is predicated on
  The degree to which the planner has properly estimated the size (e.g., KLOC) of the product to be built
  The ability to translate the size estimate into human effort, calendar time, and money
  The degree to which the project plan reflects the abilities of the software team
  The stability of both the product requirements and the environment that supports the software engineering effort

## Slide 17: Reference
Roger S. Pressman. Software Engineering, 8th edition. 2014